## 工作表1
A-Level Intelligent Mock Exam Generation System | [5 empty] | Jan | [11 empty] | Feb | [27 empty] | Mar
Task Name | Owner | Start | End | %completion | Status | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
[6 empty] | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Design Project Plan
Brainstorming | ALL | 20-Jan-25 | 23-Jan-25 | 100% | Done | bar: Week 2 20 to Week 2 23
Kickoff Meeting | ALL | 23-Jan-25 | 23-Jan-25 | 100% | Done | bar: Week 2 23
Design Gantt Chart | Mengqi Chen | 24-Jan-25 | 27-Jan-25 | 100% | Done | bar: Week 2 24 to Week 3 27
Design Risk Register | Shencong zhang | 24-Jan-25 | 27-Jan-25 | 100% | Done | bar: Week 2 24 to Week 3 27
Draft Report Outline | Ziyue Fang | 24-Jan-25 | 27-Jan-25 | 100% | Done | bar: Week 2 24 to Week 3 27
Finalize Project Plan | Aleyna Kartal | 28-Jan-25 | 31-Jan-25 | 100% | Done | bar: Week 3 28 to Week 3 31
Data Collection
Identify Data Sources | ALL | 01-Feb-25 | 02-Feb-25 | 100% | Done | bar: Week 3 1 to Week 3 2
Gather Past Exam Papers | Mengqi&Shencong&Ziyue | 03-Feb-25 | 07-Feb-25 | 100% | Done | bar: Week 4 3 to Week 4 7
Compile Notes Data | Shencong&Ale | 03-Feb-25 | 07-Feb-25 | 100% | Done | bar: Week 4 3 to Week 4 7
Extract Data from Textbooks | Mengqi&Shencong&Ziyue | 03-Feb-25 | 07-Feb-25 | 100% | Done | bar: Week 4 3 to Week 4 7
Clean Data | Shencong | 08-Feb-25 | 16-Feb-25 | 100% | Done | bar: Week 4 8 to Week 5 16
Data Annotation | Shencong | 08-Feb-25 | 16-Feb-25 | 100% | Done | bar: Week 4 8 to Week 5 16
Algorithm Development
Develop Question Selection Algorithm | Mengqi | 17-Feb-25 | 20-Feb-25 | 100% | Done | bar: Week 6 17 to Week 6 20
Code & Implement Algorithm | Ziyue | 18-Feb-25 | 26-Feb-25 | 80% | Doing | bar: Week 6 18 to Week 7 26
Unit & Integration Testing | Mengqi Chen&Shencong | 26-Feb-25 | 27-Feb-25 | 0% | Doing | bar: Week 7 26 to Week 7 27
Mid-project report & revised project plan | Ale | 25-Feb-25 | 28-Feb-25 | 0% | Done | bar: Week 7 25 to Week 7 28
Testing and Feedback
Initial System Testing | Shencong zhang Ziyue Fang | 01-Mar-25 | 09-Mar-25 | 0% | Doing | bar: Week 7 1 to Week 8 9
Performance Optimization | Shencong zhang Ziyue Fang | 10-Mar-25 | 16-Mar-25 | 0% | Not Started | bar: Week 9 10 to Week 9 16
Final Validation Testing | Shencong zhang Ziyue Fang | 17-Mar-25 | 23-Mar-25 | 0% | Not Started | bar: Week 10 17 to Week 10 23
Project Finalization
Draft & Finalize Report | ALL | 10-Mar-25 | 28-Mar-25 | 0% | Not Started | bar: Week 9 10 to Week 11 28
Develop & Practice Presentation | ALL | 24-Mar-25 | 31-Mar-25 | 0% | Not Started | bar: Week 11 24 to Week 12 31